## Source Data
Years
8th Grade | 2024 | 2025
9th Grade | 2025 | 2026
10th Grade | 2026 | 2027
11th Grade | 2027 | 2028
12th Grade | 2028 | 2029
Fall | Aug - Nov
Winter | Dec - Feb
Spring | Mar - May
Summer | Jun - Jul
More information can be found in the College Planning Calendars:
Middle School College Prep Plan
Freshman College Prep Plan
Sophomore College Prep Plan
Junior College Prep Plan
Senior College Prep Plan

## Middle School
Middle School | 2024 |  |  |  |  | 2025
Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Notes
Learn How to Homeschool High School | 2024 Aug: All Year | Resource: "Preparing to Homeschool High School" (Membership Site: How to Training)
Practice Record Keeping | 2024 Aug: All Year | Resources: Read Homeschool Record Keeping in High School https://www.homehighschoolhelp.com/homeschool-record-keeping-in-high-school
Remediate any Necessary Courses | 2024 Aug: All Year | Remember that it's always best to teach your student at their level all the time, so they can actually learn and learn to love learning.
Include any High School Level Courses on Your High School Transcript | 2024 Aug: All Year | Read Early High School Credits Earned in Middle School https://homehighschoolhelp.com/blogs/early-high-school-credits-earned-in-middle-school
Plan Your Middle School and High School Courses | 2024 Aug: All Year | Take Algebra I if possible, and other advanced classes that will prepare your child for "college prep" or advanced classes in high school. Include English, math, science, social studies, fine art, and P.E. Consider an intro to foreign language.
Research 529 Tuition Investment Plans | 2024 Aug: All Year | Resource: Read Dave Ramsey article, 10 Best Ways to Save for College https://www.ramseysolutions.com/saving/saving-for-college-is-easier-than-you-think
Estimate Financial Aid | 2024 Aug: All Year | Resource: Estimate Your Federal Student Aid https://studentaid.gov/aid-estimator/
Establish Good Study Habits | 2024 Aug: All Year

## Freshman Year
Freshman Year | 2025 |  |  |  |  | 2026
Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Notes
Keep Records | 2025 Aug: Fall | Keep high school records. Records should include work samples, tests, and papers. Keep a list of your activities, awards, community service, and other unique educational experiences throughout high school.
Plan Courses | 2025 Aug: Fall | Plan to take challenging high school courses. Read How to Wisely Plan Your High School Courses https://www.homehighschoolhelp.com/homeschool-planning-in-high-school
Start a High School Reading List | 2025 Aug: Fall | Not a bibliography, the list only needs to include author and title of books read for school and for pleasure
Make a Plan for Foreign Language | 2025 Aug: Fall | If you aren't covering a foreign language this year, make sure you do next year.
Plan College Financing | 2025 Aug: Fall | Every Year - Investigate 529 college savings plans. Resource: Dave Ramsey article, "Saving for College is Easier than You Think" http://www.daveramsey.com/blog/saving-for-college-is-easier-than-you-think/
Learn about College Scholarships | 2025 Aug: Fall | Resource: Getting The BIG Scholarships Coffee Break Book on Amazon
Decide whether Your Student Will Be Taking AP or CLEP Courses in High School | 2025 Aug: Fall | See College Planning Calendar document for additional resources. (Gold Care Club Members)
Participate in Extracurricular Activities that Develop Leadership and Teamwork | 2025 Aug: Fall | Examples include sports, drama, band, clubs, volunteer organizations, teaching others, student government (e.g. Youth in Government, Teen Pact).
Consider Summer Job or Summer Enrichment Project | 2025 Dec: Winter
Identify Preliminary List of Possible Colleges | 2025 Dec: Winter | Find out their application requirements so you will be prepared.
Determine if Your Student Should Take an AP or SAT Subject Test | 2025 Dec: Winter | For more information, watch "High school Testing" and check out College Planning Calendar document for additional resources. (Gold Care Club Members)
Register for SAT Subject Tests | 2026 Mar: Spring
Plan Courses for Next Year | 2026 Mar: Spring | Resource: The HomeScholar Planning Guide (Gold Care Club Members)
Complete the Transcript and Course Descriptions for Freshman Year | 2026 Mar: Spring
Begin College Visitations | 2026 Mar: Spring | If at all possible, try to visit college campuses. Even driving through them will give you a feel for different campus settings.
Summer Reading | 2026 Jun: Summer | Suggest books from "College Bound Reading List" http://homehighschoolhelp.com/college-bound-reading-list

## Sophomore Year
Sophomore Year | 2026 |  |  |  |  | 2027
Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Notes
High School Records | 2026 Aug: All Year | Keep high school records, including a list of activities, awards, community service, and other unique educational experiences throughout high school. Keep your receipts from the library and bookstores to fill the reading list.
Register for the PSAT For Fun | 2026 Sep: Sep | Resource: Read the article, "Take the PSAT For Fun and Profit" https://www.homehighschoolhelp.com/take-the-psat and 2 Weeks to the PSAT https://www.homehighschoolhelp.com/2-weeks-to-the-psat
Take the PSAT/NMSQT or PreACT | 2026 Oct: Oct | Sophomore year PSAT/NMSQT scores don't count for the National Merit Scholarship competition, but it's still a good idea to take the test “for fun.”
Take Challenging High School Courses | 2026 Aug: Fall | Resource: The HomeScholar Planning Guide (Gold Care Club Members)
Learn about High School Tests | 2026 Aug: Fall | Resource: Watch "High School Testing" class. Think about having your child take the PreACT (practice test for the ACT) and the PSAT. These tests are important practice tests which will prepare them for the ACT and SAT
Think about Remaining Courses that May Help You on Your ACT or SAT and Be Beneficial for College | 2026 Dec: Dec | You should receive PreSAT or PSAT results. If your child scores high, and there is a chance of competing for the National Merit Scholarship next year, then you may want to start studying for the SAT or ACT.
Continue to Plan College Financing | 2026 Dec: Winter | Investigate ways to save. Contact your financial advisor, and research college 529 Savings Plans. Read Planning for College While You’re Still in High School https://www.ramseysolutions.com/saving/planning-for-college
Take Sample SAT and ACT Tests | 2026 Dec: Winter | Determine if your student will score better on the SAT or ACT. The only way to really know is for your student to take a sample of each test. Resources in the article College Admission Tests https://www.homehighschoolhelp.com/college-admission-tests
Apply for Summer Job or Summer Enrichment Program | 2026 Dec: Winter
Update Your Child's Reading List | 2026 Dec: Winter | Include all books you purchased, assigned for school, or read from the library.
College Planning | 2027 Mar: Spring | Begin to look at college catalogs, web sites, and other information. You can view the video on Finding a College as well. If at all possible, register for official college visits this spring.
Learn about Financial Aid with Scholarships | 2027 Mar: Spring | Read Homeschool Scholarships for College - How Homeschoolers Earn Scholarships https://www.homehighschoolhelp.com/homeschool-scholarships-for-college and watch "Getting the BIG Scholarships" video
Learn about the FAFSA | 2027 Mar: Spring | Read: 9 Secrets to Effortlessy Finish the FAFSA http://homehighschoolhelp.com/9-secrets-to-effortlessly-finish-the-fafsa Find your "Expected Family Contribution" but remember it does NOT include merit scholarships, only need-based aid. Resource: Estimate Your Federal Student Aid https://studentaid.gov/aid-estimator/
Finalize your Reading List for the Year | 2027 Jun: Jun | This is a list, not a bibliography, so it only needs to contain the title and author.
Finalize Sophomore Transcript | 2027 Jun: Jun | Complete the transcript (and course descriptions) for your student's sophomore year.
Summer Reading List | 2027 Jun: Jun | Suggest summer reading from my article, "College Bound Reading List." Include any summer reading on the reading list for sophomore or junior year.

## Junior Year
Junior Year | 2027 |  |  |  |  | 2028
Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Notes
High School Record Keeping | 2027 Aug: All Year | Keep high school records, including a list of your activities, awards, community service, and other unique educational experiences throughout high school.
Attend College Fairs | 2027 Aug: All Year | Ask questions about financial aid as well as the academic program, and student life. Find out if colleges require SAT, ACT, or AP (Advanced Placement) exams. If they require these tests, find out how to prepare and register for them.
Take Challenging High School Courses | 2027 Aug: Fall
Read about Junior Year | 2027 Sep: Sep | Read "The 9 Keys to a Successful Junior Year," for an overview of important tasks that you must complete this year: http://homehighschoolhelp.com/the-9-keys-to-a-successful-junior-year
Register for the PSAT | 2027 Sep: Sep | Register for the PSAT. Find out about the PSAT/NMSQT test, date, time, and test location in October.
Register for AP Exams, as Appropriate | 2027 Sep: Sep | These exams test academic subjects that have been completed. If needed, it's a good idea to take these tests during junior year, so the scores are available to colleges when you apply in the fall.
Take Challenging High School Courses | 2027 Sep: Sep | Have you taken or planned for foreign language? Have you completed at least one art class?
Take the PSAT/NMSQT | 2027 Oct: Oct | Take the PSAT/NMSQT to be eligible for the National Merit Scholarship. Make sure your child has slept well, eaten a good breakfast, and takes snacks and water to the test with them. Send a calculator they are comfortable using, and more than enough sharp pencils.
Finalize SAT or ACT Test Decision | 2027 Nov: Nov | Decide whether your child should take the SAT or ACT test for college admission. Give a sample of each test while you are at home. Identify which test will provide the best score for your child. Then develop a study plan for that test. Resources: Recommended Study Guides for High School Test Prep https://www.homehighschoolhelp.com/blogs/recommended-study-guides-for-high-school-test-prep
Use "Researching Scholarships" as an English Credit | 2027 Nov: Nov | Consider searching for scholarships as the basis for your English credit this year. Resource: Read the Coffee Break Book, College Scholarships for High School Credit.
Learn about the College Admission and Scholarship Process | 2027 Nov: Nov | Learn about the college admission and scholarship process, so you can make a strategy for your year. Your goal is to choose colleges where you want your child to apply for admission. At this stage, it's helpful to watch my videos geared toward planning for college admission. Resources: "Finding a College" and "Getting the BIG Scholarships" (Gold Care Club Members)
Determine if SAT II or AP Exams are required | 2027 Nov: Nov | Find out if your child will need SAT Subject Tests, and/or AP exams, which will depend on where they apply to college. Then learn about how to register and study for those tests here: The College Board: https://www.collegeboard.org/
Decide if You Want to Pursue AP or CLEP for College Credit | 2027 Nov: Nov | Decide if you want to pursue AP or CLEP for college credit, if applicable, and learn more about how to take those tests. Resources: Read the article, "Homeschool College This Summer" http://homehighschoolhelp.com/homeschool-college-this-summer
Receive and Analyze the Results of the PSAT/NMSQT | 2027 Dec: Dec | Receive the results of the PSAT/NMSQT in December. Read the score report and determine how your child might improve. Register and take SAT or ACT.
Make a List of Colleges You Would Like to Explore | 2027 Dec: Dec
Start Research on Government and Private, Financial Aid Programs | 2028 Jan: Jan | Continue to plan college financing.
Register for SAT or AP Exams | 2027 Dec: Winter
Plan College Visits | 2027 Dec: Winter | This is a critical step in determining the right college, because you can't know everything about a college just by their statistics and promotional materials. Arrange your visit by contacting the college admission department.
Spring College Fair Planning | 2027 Dec: Winter | Be sure to ask questions about financial aid, as well as the academic program and student life.
Fill out FAFSA Estimate | 2027 Dec: Winter | Remember that the FAFSA is only an estimate of need-based financial aid, not the financial aid you will receive based on merit. Learn About the FAFSA, 9 Secrets to Effortlessly Finish the FAFSA: https://www.homehighschoolhelp.com/fafsa-application-for-homeschoolers
Practice College Application Essays | 2027 Dec: Winter | For every college where you plan to apply, find their application online. On the application form, you will find application essays. Collect essay prompts, and practice with them as part of your junior year writing plan.
Send Letters or Emails to Colleges on Your List | 2027 Dec: Winter | Begin to make a list of 15-20 colleges you would like to explore. Send letters or emails to colleges on your list requesting information, and evaluate the materials they send.
Sign up for the SAT or ACT Tests | 2027 Dec: Winter | If you haven’t already done so, sign up for the March or June tests for the SAT or ACT.
Start planning your Summer activities | 2027 Dec: Winter | Help your child create a resume for job applications and look for a summer job, internship, camp, or activity. They can consider enrolling in an academic college course, pursuing a summer school program, or working as a volunteer. If they work over the summer, encourage them to put aside some of the money for college.
Visit Colleges | 2028 Mar: Spring | Try to visit colleges when classes are in session. Call the college admissions office before you visit the campus. The admissions staff will schedule you for a campus tour, arrange an interview, and schedule an appointment with a financial aid counselor to learn more about the college's financial aid opportunities.
Last Chance to Sign up for the May/June SAT and ACT | 2028 Mar: Spring
Take the SAT or ACT early spring | 2028 Mar: Spring
Evaluate Colleges and Narrow Your Choices | 2028 Mar: Spring
Take SAT or ACT late spring | 2028 Mar: Spring
Compare College Statistics | 2028 Mar: Spring | Find Books Comparing College Statistics here: https://www.homehighschoolhelp.com/blogs/books-comparing-college-statistics
Complete Your Transcript (and Course Descriptions) for Your Student's Junior Year | 2028 Jun: Summer | Update all homeschool records, including your child's reading list. This is a list, not a bibliography, so it only needs to contain the title and author.
Work on College Application Essays | 2028 Jun: Summer | If you're interested in an athletic scholarship, contact coaches at colleges where you plan to apply. If the schools or scholarships you are interested in require it, begin to assemble writing samples, portfolios, or audition tapes.
Read Books from "College Bound Reading List" | 2028 Jun: Summer | Read books from my article, "College Bound Reading List" and include them on the high school reading list.

## Senior Year
Senior Year | 2028 |  |  |  |  | 2029
Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Notes
Finish the High School Records | 2028 Aug: Fall | Keep high school records, including a list of activities, awards, community service, and other unique educational experiences throughout high school. This must be submitted with college applications.
Take Challenging High School Courses | 2028 Aug: Fall | Resource: The HomeScholar Planning Guide (Gold Care Club Members)
If Necessary, Take or Retake the first available SAT or ACT this fall. | 2028 Aug: Fall | If your child has not already taken admission tests, or if you feel they can improve their scores, register to take or retake the October/November SAT or October ACT.
Begin College Applications the first day of senior year. They take a LONG time. | 2028 Aug: Fall | Evaluate college plans in light of test scores and junior year grades. Choose 4-8 colleges where your student will apply. If needed, attend a regional college fair to further investigate colleges on your list.
Request Information from Colleges | 2028 Aug: Fall | Write to colleges on your list and request admission, financial aid, and housing applications, if appropriate.
Organize your applications | 2028 Sep: Sep | Make a Calendar for Test Dates, Due Dates, Deadlines, and Fees
Register for AP Exams if needed | 2028 Sep: Sep
Continue to Plan College Financing | 2028 Sep: Sep | Investigate 529 college savings plans.
Obtain Letters of Recommendation to Mail to Colleges | 2028 Sep: Sep | Give recommendation writers any forms colleges require and follow up to make sure the letters are mailed on time.
Write College Application Essays | 2028 Sep: Sep | Apply for early admission (preferable). Be sure to keep copies of everything you send, with the date on which it was mailed.
Begin Searching for College Scholarships | 2028 Sep: Sep
Obtain FSA ID | 2028 Sep: Sep | Read the Government Website here https://studentaid.gov/h/apply-for-aid/fafsa
Parents complete the FAFSA on October 1st | 2028 Oct: Oct | Work to complete the FAFSA on or as soon after October 1 as possible. If the financial aid processor requests additional information in order to process your application, submit it promptly. Determine whether your state student aid program requires an additional application.
Complete all applications before Thanksgiving. | 2028 Nov: Nov
Review Your Student Aid Report | 2028 Nov: Nov | Review your Student Aid Report from the FAFSA for accuracy.
File Your Last College Applications (regular admission) | 2028 Dec: Winter | If you've applied for early decision, you should have an answer by now.
Send 1st Semester Transcript to Colleges | 2029 Jan: Jan | Send the transcript with first semester grades to colleges where you've applied. Make sure to include your planned graduation date.
Senior Picture | 2029 Feb: Feb/Mar | Senior pictures are often included with graduation announcements.
Graduation Party Prep | 2029 Feb: Feb | Go to HomeschoolDiploma.com to get a diploma, cap and gown, announcements, and invitations.
Tax Credit | 2029 Feb: Feb | Check with your accountant about tax credits when filing taxes.
Monitor Your Application Status | 2029 Feb: Feb | Monitor applications to make sure all materials are sent and received on time.
Summer Employment Job Search | 2029 Feb: Feb/Mar | Have your student look for a job for the summer. Encourage them to save a portion of those earnings for college.
Financial Aid Analysis | 2029 Mar: Spring | Review financial aid award letters together; be sure that you understand the terms and conditions that apply to each type of aid offered. Compare financial offers from each college – looking closely at the actual cost out of your pocket.
College Selection | 2029 Mar: Mar / Apr | Decide on the one college your child will attend and send in your tuition deposit. Notify other colleges that accepted your child that you have selected another school, in writing. Be sure to respond by May 1. If your first choice college places your child on its waiting list, do not lose all hope. Some students are admitted off the waiting list. Contact the college to let the admissions office know you are still very interested, and keep the college updated on your activities.
Final College Decision before May 1st | 2029 Apr: Apr | Make the final decision on college choice. May 1st is the National Candidate Reply Date. Your child has to make their final college decision by May 1st.
Take Advanced Placement Exams | 2029 May: May
On-Campus Housing/Meal plan application | 2029 May: May | If your child will live on campus, complete a housing/meal plan application.
On-Campus Budget Plan - Books Supplies, Living Expenses | 2029 May: May | Determine how much grants and scholarships will cover, and how much the student and parents will contribute.
Final Transcript Update | 2029 Jun: Jun | Send a copy of the final transcript to the college your child will attend. Make sure it includes the graduation date. Notify the college of any private grants or scholarships your child will receive.
Document Payment Schedule | 2029 Jun: Jun | Find out when payment for tuition and room and board are due.
Graduation Party! | 2029 Jun: Jun | Celebrate this huge milestone! Present their high school diploma
Dorm Room Supplies - As Needed | 2029 Jun: Jun | Identify and purchase what your child needs for the college dorm room.
Student should Call or Email College Roommate | 2029 Jun: Summer
Apply and Confirm Freshman Housing | 2029 Jun: Summer
Prep for Life on Campus | 2029 Jul: Jul | Look for information from the new college about housing, orientation, and registering for classes. If the financial aid package included a Federal Work-Study award, it may be your child's responsibility to find an appropriate job. Plan to follow up with the financial aid office as soon as your child arrives on campus.
Pack for College - Aug/Sep | [12 empty] | Look forward to a great experience.